## HSR timeline
Health Star Rating (HSR) - Five Year Review
Activity | Q4 2016 | Q1 2017 | Q2 2017 | Q3 2017 | Q4 2017 | Q1 2018 | Q2 2018 | Q3 2018 | Q4 2018 | Q1 2019 | Q2 2019 | Q3 2019 | Q4 2019
HSR 5 year review
Planning - Terms of Reference | Developed (HSRAC) | Endorsed (HSRAC & FRSC) | Endorsed (Forum)
Planning - Statement of Requirement |  | Endorsed (HSRAC)
Reviewer |  | Engage reviewer |  | Planning review | Collecting data and consulting Summary report on submissions to the five year review - 15/10/17 Navigation paper - 15/01/18 Summary report of outcomes from consultations - 30/04/18 |  |  |  | System enhancements consultation paper open for public consultation 12/10-07/12 | Public consultation on draft five year review report | Delivery of report to HSRAC, FRSC and Forum | FRSC and Forum consideration of report
Heart Foundation - Final report
NZ MPI - Final report
Form of the food ('as prepared') rules reappraisal
HSRAC endorsement
Call out to industry for data/validation |  |  | Input received
Discussion paper |  |  | HSRAC discussion paper
Consultation |  |  | Public submissions - discussion paper: 19 May-30 June 2017 | Stakeholder workshops - discussion paper |  |  | Stakeholder workshops - options paper
Data collection and analysis |  |  |  | Analysis of submissions and feedback from workshops
Options paper |  |  |  |  | Results provided to TAG for options modelling; HSRAC paper with options developed |  | Provision of outcomes to reviewer
Revision of rule (if required) | [6 empty] | Recommendations to HSRAC, FRSC and Forum | Industry notification to be implemented alongside outcome of five year review
Stakeholder engagement / Consultation
Workshops | NZ 11/10/16 |  |  | As Prepared: 28/09 Sydney | As Prepared: 05/10 Auckland 12/10 Melbourne |  | As Prepared: 23/04 Melbourne 24/04 Sydney |  | Five year review: 14/11 Sydney 16/11 Auckland 19/11 Melbourne
Public consultation process |  |  | 8 June-20 July 2017 |  |  | 02/02 Adel, 07/02 Syd, 21/02 Melb, 01/03 Bris, 08/03 Auckland, 19/03 Perth | 12/04 Canb |  | System enhancements consultation paper open for public consultation 12/10-07/12 | Public consultation on draft five year review report 25/02-24/03
Targeted meetings | 25/11 - Public Health Orgs (Sydney) 15/12 - Dietitians workshop (Adelaide) |  | Industry research forum |  | 27/11 PHAA forum, Canberra 30/11 Dairy Australia forum, Melbourne
Reporting
2 year report to FRSC |  | 2017-02-24
2 year report to Forum |  |  | 2017-04-28
FRSC update |  | 2017-02-24 |  | 2017-09-22 |  |  | 2018-05-17 |  | 2018-11-01
Forum update |  |  | 2017-04-28 |  | 2017-11-24 |  | 2018-06-29 |  | 2018-12-14
5 Year Review report to FRSC
5 Year Review report to Forum
AHMAC - social marketing funding |  | 2017-02-17
Uptake figures release dates |  |  | 27/04 |  | 28/10 | 29/01 FoodTrack, AoE2 | 27/04 FoodTrack, in-store, AoE2 | 13/07 FoodTrack 24/08 AoE2 |  | 28/02 in-store |  | 29/07 in-store 23/08 FoodTrack
HSRAC
Meetings | 2016-11-18 | 2017-02-14 | 2017-05-09 | 08/08 & 27/09 | 11/10, 15/11 & 14/12 | 13/02 & 27/03 | 18/05 & 26/06 | 09/08 & 25/09 | 13/11 & 11/12 | 2019-02-08 | 9/04/2019 tbc/06/2019
SMAG
Reporting to HSRAC |  | 2017-02-14 |  |  |  | 2018-02-13 | 2018-05-18 |  | 2018-11-13 | 2019-02-08 | 9/04/2018 tbc/06/2019
Meetings | 2016-11-16 | 2017-01-25 | 2017-06-08 |  | 2017-12-07
Social marketing phases |  | Phase 4 | [7 empty] | Phase 5
Campaign evaluation reports |  |  | 2017-09-01 | [7 empty] | Proposed
TAG
Reporting to HSRAC |  | 2017-02-14 |  |  | 2017-12-14 | 2018-02-13 | 2018-05-18 | 2018-08-09
Meetings | 18/10 & 13/12 | 2017-01-31 | 2017-06-30 | 4/08 & 12/09 | 13/11 & 5/12 | 31/01, 06/03 | 06/04, 01/05 & 05/06 | 10/07, 09/08 & 28/08
Algorithm review
Key: AHMAC - Australian Health Ministers' Advisory Council Forum - Australia and New Zealand Ministerial Forum on Food Regulation FRSC - Food Regulation Standing Committee Heart Foundation - National Heart Foundation of Australia HSR - Health Star Rating HSRAC - HSR Advisory Committee NZ MPI - New Zealand Ministry for Primary Industries SMAG - Social Marketing Advisory Group TAG - Technical Advisory Group